## Online Gantt 20260304
Outline Level | ID | Name | Start | Finish | Duration | % Complete | Predecessors | Resource Names | Column1 | Notes
1 | 1 | Use-Case Diagrams | 2026-03-02 | 2026-03-06 | 5 days | 0 |  | Full Team |  | Diagrams that showcase the relations between Use-Cases and Actors
1 | 2 | UML Class Diagrams | 2026-03-09 | 2026-03-13 | 5 days | 0 | 1FS | Full Team |  | Diagrams that showcase the relations between the Class candidates
1 | 3 | UML Sequence Diagram | 2026-03-16 | 2026-03-20 | 5 days | 0 | 2FS | Full Team |  | Diagrams that showcase the relations between Classes and Actors
1 | 4 | Design Presentation Prep | 2026-03-23 | 2026-03-27 | 5 days | 0 | 3FS | Full Team |  | Team Preparation for Presentation
1 | 5 | Client Module Implementation Initialization | 2026-03-30 | 2026-04-07 | 7 days | 0 | 4FS | Darien,Victor |  | Implementation Initialization. The deliverable by the end of this week is dependency level classes. Any classes that require other classes' implementation should be done. Next week will expect full whitebox testing, and at minimum an 80% functional CLI interface with the application
1 | 6 | Server Module Implementation Initialization | 2026-03-30 | 2026-04-07 | 7 days | 0 | 4FS | Ola,Clarize |  | Implementation Initialization. The deliverable by the end of this week is dependency level classes. Any classes that require other classes' implementation should be done. Next week will expect a full whitebox testable application for all the classes, as well as a 90% complete CLI with the application.
1 | 7 | Client Module Implementation | 2026-04-08 | 2026-04-16 | 7 days | 0 | 5FS | Darien,Victor |  | Functional Application. By this point, the application runs, perhaps missing a few features or logistical errors. There should be a driver that contains ALL the white-box testing of the application. At minimum there's a CLI with the application to work with. Next week will expect integration between the Client and the Server. Any bugs, errors, exceptions should be mitigated by that point.
1 | 8 | Server Module Implementation | 2026-04-08 | 2026-04-16 | 7 days | 0 | 6FS | Ola,Clarize |  | Functional Application. By this point, the application runs, perhaps missing a few features or logistical errors. There should be a driver that contains ALL the white-box testing of the application. At minimum there's a CLI with the application to work with. Next week will expect integration between the Client and the Server. Any exceptions, bugs, or errors should be mitigated by that point.
1 | 9 | Client Module Implementation Integration | 2026-04-17 | 2026-04-27 | 7 days | 0 | 7FS | Darien,Victor |  | Fully Functional Standalone Application. Get the Project Space for the Client Organized. By this point, there are no program crashes, full exception handling, and full whitebox as well as black box testing using a CLI or GUI. The application now must be put together, communicating over a network seamlessly, testing all features. Before next time, is to stress test even further than what was done in the whitebox/blackbox, as well as prepare for the Final Presentation. If something breaks, this is the week to debug and fix it.
1 | 10 | Server Module Implementation Integration | 2026-04-17 | 2026-04-27 | 7 days | 0 | 8FS | Ola,Clarize |  | Fully Functional Standalone Application. Get the Project Space for the Client Organized. By this point, there are no program crashes, full exception handling, and full whitebox as well as black box testing using a CLI or GUI. The application now must be put together, communicating over a network seamlessly, testing all features. Before next time, is to stress test even further than what was done in the whitebox/blackbox, as well as prepare for the Final Presentation. If something breaks, this is the week to debug and fix it.
1 | 11 | Final Presentation Prep | 2026-04-28 | 2026-05-06 | 7 days | 0 | 10FS | Full Team |  | Team Preparation for Presentation and Demonstration